## Gantt Chart
GANTT CHART: DSI Project 4
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER(S) | PERCENT COMPLETE | WEEK 1 | WEEK 2
DSI Project 4: Predicting The Presence of West Nile Virus
| Outside Research | 2022-08-01 | 2022-08-04 | 0 | 4 | JiaQing | 100%
| Preliminary data cleaning | 2022-08-01 | 2022-08-02 | 0 | 2 | All | 100%
| Discuss and conduct data cleaning | 2022-08-03 | 2022-08-04 | 2 | 2 | All | 100%
| Discuss and conduct EDA | 2022-08-04 | 2022-08-07 | 3 | 4 | Wende | 100%
| Modeling | 2022-08-08 | 2022-08-11 | 7 | 4 | Hao Han | 100%
| Discuss and refine modeling results | 2022-08-10 | 2022-08-11 | 9 | 2 | All | 100%
| Cost Benefit Analysis | 2022-08-10 | 2022-08-11 | 9 | 2 | All | 100%
| Readme | 2022-08-12 | 2022-08-12 | 11 | 1 | All | 100%
| Slides and final notebooks | 2022-08-12 | 2022-08-12 | 11 | 1 | All | 100%
| Project submission and presentation | 2022-08-15 | 2022-08-15 | 14 | 1 | All | 100%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1